## Task Tracker
TASK TRACKER
Name: | Kathan Parikh |  |  |  | Date:
TASK TITLE | STATUS | PRIORITY | START DATE | DUE DATE | PCT OF TASK COMPLETE | COMMENTS | STATUS MENU | PRIORITY MENU
Understanding project requirement | ☒ | MEDIUM | 2020-07-27 | 2020-07-27 | 100% |  | ☐ | HIGH
Decided the workflow and started to figuring out what tables and entities will be required | ☒ | HIGH | 2020-07-28 | 2020-07-28 | 100% |  | ☒ | MEDIUM
Divided the work and started creating tables individually | ☐ | MEDIUM | 01-08-2020 | 02-08-2020 | 70% |  |  | LOW
Completed the tables individually and connected them in order to create EER Diagram | ☒ | MEDIUM | 02-08-2020 | 02-08-2020 | 100% | Tables that I created : Song, Order ,Product , Product_Type
CREATED QUERIES 5-7 + 2 ADDITIONAL QUERIES | ☐ | HIGH | 03-08-2020 | 04-08-2020 | 70%
COMPLETED QUERIES 5-7 + 2 ADDITIONAL QUERIES | ☒ | HIGH | 04-08-2020 | 04-08-2020 | 100%
CREATED STORED PROCEDURE | ☒ | HIGH | 10-08-2020 | 10-08-2020 | 100%
TESTED THE WHOLE PROJECT (FINAL CHECK - QUERIES, STORE PROCEDURES, TABLES) | ☒ | MEDIUM | 11-08-2020 | 11-08-2020 | 100%
STARTED CREATING POWERPOINT PRESENTATION | ☐ | MEDIUM | 14-08-2020 | 16-08-2020 | 40%
COMPLETED CREATING POWERPOINT PRESENTATION | ☒ | MEDIUM | 15-08-2020 | 16-08-2020 | 100%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%